## Sheet1
Job No | Stage | Date | Fitter | Notes
J-26S-001 | Quote Sent | 04/03/2026 | Mark Deehan | ok
J-26S-001 | Quote Accepted | 08/03/2026 | Paddy Lynch | ok
J-26S-001 | SITE SURVEY | 10/03/2026 | Ciara McCrossan | Done
J-26S-001 | Site Survey | 12/03/2026 | Mark Deehan | ok
J-26S-001 | Materials Ordered | 14/03/2026 | Mark Deehan | done
J-26S-001 | Site Work Started | 17/03/2026 | Paddy Lynch | done
J-26S-001 | snagging | 22/03/2026 | Mark Deehan | Done
J-26S-001 | invoice sent | 23/03/2026 | Ciara McCrossan | Done
J-26S-001 | PAYMENT RECEIVED | 30/03/2026 | Ciara McCrossan | complete
J-26S-003 | quote sent | 09/03/2026 | Paddy Lynch | ok
J-26S-003 | Quote Accepted | 13/03/2026 | Ciara McCrossan | Done
J-26S-003 | SITE SURVEY | 15/03/2026 | Mark Deehan | ok
J-26S-003 | Materials Ordered | 16/03/2026 | Mark Deehan | complete
J-26S-005 | Quote Sent | 10/03/2026 | Mark Deehan | Done
J-26S-005 | Quote Accepted | 14/03/2026 | Paddy Lynch | complete
J-26S-005 | Site Survey | 17/03/2026 | Paddy Lynch | done
J-26S-005 | MATERIALS ORDERED | 18/03/2026 | Paddy Lynch | ok
J-26S-005 | Site Work Started | 21/03/2026 | Mark Deehan | Done
J-26S-005 | snagging | 23/03/2026 | Ciara McCrossan | ok
J-26S-005 | INVOICE SENT | 24/03/2026 | Ciara McCrossan | sorted
J-26S-005 | payment received | 30/03/2026 | Mark Deehan | complete
J-26S-007 | QUOTE SENT | 18/03/2026 | Paddy Lynch | done
J-26S-007 | Quote Accepted | 23/03/2026 | Ciara McCrossan | complete
J-26S-007 | site survey | 26/03/2026 | Ciara McCrossan | done
J-26S-007 | site survey | 28/03/2026 | Mark Deehan | supplier late
J-26S-009 | quote sent | 24/03/2026 | Mark Deehan | Done
J-26S-009 | QUOTE ACCEPTED | 27/03/2026 | Paddy Lynch | complete
J-26S-009 | SITE SURVEY | 30/03/2026 | Ciara McCrossan | ok