## Sheet1
Job # | Phase | When | Who | Comments
J-26S-002 | quote sent | 2026-03-06 | Ciara McCrossan | complete
J-26S-002 | Quote Accepted | 2026-03-10 | Paddy Lynch | Done
J-26S-002 | Site Survey | 2026-03-13 | Ciara McCrossan | sorted
J-26S-002 | MATERIALS ORDERED | 2026-03-16 | Mark Deehan | Done
J-26S-002 | site work started | 2026-04-01 | Ciara McCrossan | ok
J-26S-002 | Snagging | 2026-04-04 | Mark Deehan | done
J-26S-002 | Invoice Sent | 2026-04-06 | Ciara McCrossan | complete
J-26S-002 | payment received | 2026-04-13 | Ciara McCrossan | complete
J-26S-004 | QUOTE SENT | 2026-03-09 | Ciara McCrossan | done
J-26S-004 | Quote Accepted | 2026-03-14 | Paddy Lynch | done
J-26S-004 | Site Survey | 2026-03-16 | Mark Deehan | done
J-26S-004 | materials ordered | 2026-03-17 | Paddy Lynch | ok
J-26S-004 | Site Work Started | 2026-03-18 | Paddy Lynch | Done
J-26S-004 | Snagging | 2026-03-20 | Ciara McCrossan | ok
J-26S-004 | SITE WORK STARTED | 2026-03-24 | Paddy Lynch | tbc
J-26S-004 | Invoice Sent | 2026-03-25 | Mark Deehan | done
J-26S-004 | payment received | 2026-03-31 | Ciara McCrossan | sorted
J-26S-006 | Quote Sent | 2026-03-19 | Mark Deehan | sorted
J-26S-006 | Quote Accepted | 2026-03-22 | Mark Deehan | sorted
J-26S-006 | Site Survey | 2026-03-25 | Mark Deehan | sorted
J-26S-006 | materials ordered | 2026-03-28 | Paddy Lynch | ok
J-26S-006 | SITE WORK STARTED | 2026-03-31 | Ciara McCrossan | ok
J-26S-006 | snagging | 2026-04-04 | Mark Deehan | Done
J-26S-006 | Site Work Started | 2026-04-07 | Mark Deehan | sorted
J-26S-006 | Invoice Sent | 2026-04-10 | Paddy Lynch | complete
J-26S-006 | payment received | 2026-04-16 | Paddy Lynch | complete
J-26S-008 | quote sent | 2026-03-24 | Ciara McCrossan | Done
J-26S-008 | QUOTE ACCEPTED | 2026-03-26 | Ciara McCrossan | ok
J-26S-008 | site survey | 2026-03-28 | Paddy Lynch | done
J-26S-008 | MATERIALS ORDERED | 2026-03-31 | Mark Deehan | done
J-26S-008 | SITE WORK STARTED | 2026-04-17 | Mark Deehan | Done
J-26S-008 | snagging | 2026-04-20 | Paddy Lynch | complete
J-26S-008 | Invoice Sent | 2026-04-23 | Mark Deehan | ok
J-26S-010 | Quote Sent | 2026-04-02 | Mark Deehan | done
J-26S-010 | Quote Accepted | 2026-04-06 | Paddy Lynch | Done
J-26S-010 | Site Survey | 2026-04-09 | Paddy Lynch | Done
J-26S-010 | site survey | 2026-04-11 | Paddy Lynch | waiting on glass
J-26S-010 | Materials Ordered | 2026-04-12 | Paddy Lynch | ok
J-26S-010 | Site Work Started | 2026-04-14 | Ciara McCrossan | ok
J-26S-010 | SNAGGING | 2026-04-19 | Paddy Lynch | Done
J-26S-010 | Invoice Sent | 2026-04-22 | Mark Deehan | sorted
J-26S-010 | Payment Received | 2026-04-25 | Ciara McCrossan | sorted
J-26S-012 | quote sent | 2026-04-01 | Ciara McCrossan | done
J-26S-012 | QUOTE ACCEPTED | 2026-04-04 | Mark Deehan | Done
J-26S-012 | Site Survey | 2026-04-07 | Ciara McCrossan | complete
J-26S-012 | Materials Ordered | 2026-04-09 | Ciara McCrossan | done
J-26S-012 | Site Work Started | 2026-04-10 | Ciara McCrossan | sorted
J-26S-012 | snagging | 2026-04-12 | Paddy Lynch | ok
J-26S-012 | Invoice Sent | 2026-04-15 | Ciara McCrossan | done
J-26S-012 | Payment Received | 2026-04-19 | Ciara McCrossan | Done
J-26S-014 | QUOTE SENT | 2026-04-06 | Mark Deehan | Done
J-26S-014 | Quote Accepted | 2026-04-08 | Ciara McCrossan | Done
J-26S-014 | SITE SURVEY | 2026-04-09 | Mark Deehan | complete
J-26S-014 | Materials Ordered | 2026-04-12 | Ciara McCrossan | Done
J-26S-014 | Site Work Started | 2026-04-13 | Paddy Lynch | done
J-26S-014 | Snagging | 2026-04-16 | Paddy Lynch | done
J-26S-014 | INVOICE SENT | 2026-04-19 | Mark Deehan | complete
J-26S-014 | Payment Received | 2026-04-25 | Mark Deehan | Done